## Blank template
Construction site diary
BLANK TEMPLATE
Daily record · work, resources and notable events
Project / site
Date / report no.
Prepared by / role
Weather / temperature
Working hours / interruption
Area / construction phase
1 · Work performed and personnel
Company / trade | People / hours |  | Work / area / progress
2 · Equipment, deliveries and records
Type / quantity |  | Use / delivery / record
3 · Deviations, agreements and next steps
Event / finding |  |  | Action / owner / due date
Prepared / date: ____________________ Reviewed / date: ____________________
Adapt to the project and obtain a competent professional review before use. Record only necessary personal data and store it securely.

## Example
Construction site diary
SYNTHETIC EXAMPLE
Daily record · work, resources and notable events
Project / site |  | Example site A (fictional)
Date / report no. |  | 15.04.2026 / DEMO-01
Prepared by / role |  | Person A / site manager (fictional)
Weather / temperature |  | Cloudy / 12 °C (example)
Working hours / interruption |  | 07:00–16:00 / 12:00–12:30
Area / construction phase |  | Section A / internal fit-out
1 · Work performed and personnel
Company / trade | People / hours |  | Work / area / progress
Example company A / drywall | 3 / 8,5 h |  | Section A: framing started; grid lines 1–3 completed.
2 · Equipment, deliveries and records
Type / quantity |  | Use / delivery / record
1 material delivery |  | Framing profiles, delivery note DEMO-L1; received 09:10.
3 · Deviations, agreements and next steps
Event / finding |  |  | Action / owner / due date
Delivery area temporarily occupied; 20-minute delay. |  |  | Coordinate next day's delivery with example company B; Person A; 15 Apr.
Prepared / date: ____________________ Reviewed / date: ____________________
Adapt to the project and obtain a competent professional review before use. Record only necessary personal data and store it securely.
All entries are fictional; this example is not an approved work instruction.

## Notes
Use and review
Copy the blank template for each working day. Record observed facts, times and parties; mark unknown information as open.
Add unique references for photos, drawings and delivery notes. Make agreements and changes traceable; check contractual requirements.
Adapt to the project and obtain a competent professional review before use. Record only necessary personal data and store it securely.
All entries are fictional; this example is not an approved work instruction.
sigeko.app · Work aid 1.0