## Blank template
Safety and health plan · work aid
BLANK TEMPLATE
Coordination of trades, construction sequence and shared facilities
Project / site
Client / representative
Coordinator / prepared by
Plan status / version / date
Schedule / phase covered
Related drawings / rules
1 · Coordination across trades (add rows / sheets as needed)
ID / area | Trade / activity | Period / overlap | Hazard / interaction | Control / coordination rule | Owner / provision | Review / deadline / evidence
Prepared / date: ____________________ Reviewed / date: ____________________
This table is a work aid, not a complete safety and health plan or a guarantee of legal compliance. A competent professional must develop, review and update the project-specific plan.
Adapt to the project and obtain a competent professional review before use. Record only necessary personal data and store it securely.

## Example
Safety and health plan · work aid
SYNTHETIC EXAMPLE
Coordination of trades, construction sequence and shared facilities
Project / site |  |  | Example site A (fictional)
Client / representative |  |  | Example client (fictional)
Coordinator / prepared by |  |  | Person A (fictional)
Plan status / version / date |  |  | DEMO / 0.1 / 15.04.2026
Schedule / phase covered |  |  | 15.04.–30.04.2026 / A
Related drawings / rules |  |  | Site layout drawing DEMO-P1
1 · Coordination across trades (add rows / sheets as needed)
ID / area | Trade / activity | Period / overlap |  | Hazard / interaction | Control / coordination rule | Owner / provision | Review / deadline / evidence
01 / A | Scaffolding; facade work | 15–16 Apr 2026; planned overlap |  | Overlapping work areas; falling objects during scaffold assembly. | Separate work in time; cordon off assembly area; agree access with affected parties before work resumes. | Example company A: barrier; Person A: coordination | Before work; verify responsibility and effectiveness on site; DEMO-P1
Prepared / date: ____________________ Reviewed / date: ____________________
This table is a work aid, not a complete safety and health plan or a guarantee of legal compliance. A competent professional must develop, review and update the project-specific plan.
Adapt to the project and obtain a competent professional review before use. Record only necessary personal data and store it securely.
All entries are fictional; this example is not an approved work instruction.

## Notes
Use and review
This table is a work aid, not a complete safety and health plan or a guarantee of legal compliance. A competent professional must develop, review and update the project-specific plan.
Add project-specific sequencing, spatial and timing interactions, particularly hazardous work, shared facilities, responsibilities and relevant requirements. The example is deliberately incomplete.
Document distribution / coordination with parties, changes and related drawings separately. Check that controls are suitable and implemented on site.
Adapt to the project and obtain a competent professional review before use. Record only necessary personal data and store it securely.
All entries are fictional; this example is not an approved work instruction.
sigeko.app · Work aid 1.0